| Title: Magee, OL 101 Assignment Seven - Logframe Template to Fill In |
| --- |
| Date: |
| OL 101 Assignment Seven Student Logframe Template to Fill In - Annotated |
| 100 Mayan families will enjoy improved health, nutrition and food security through a health, family garden and nutrition project. |
| Problem Statement | [Problems and underlying causes] (1) 300 small children from 100 families in four Guatemalan villages are frequently ill with chronic diarrhea caused by little knowledge of health and hygiene, and (2) chronically undernourished caused by little knowledge of nutrition, and a shortage of food reserves which contribute to [Negative Impacts] (a) stunting (reduced physical and mental development) that affects participation in (b) family/community activity and (c) school attendance thereby reducing their ability to receive an education. This leads to a reduction in their ability as adults to (d) lead the productive, meaningful, prosperous lives they need to leave the cycle of poverty and contribute to the development of their communities. |
|  |  |  |  | Objectively Verifiable Indicators | Means of Verification |  |
| Goal [Short-term and medium–term outcomes of the activities/outputs/sub-goals of the project] | 300 small children of 100 families in four villages in the Western Highlands of Guatemala will be able to [Underlying causes to problems as if they have been solved] (1) enjoy better health through a health and hygiene program, (2) and improved nutrition and 12 months of food security per year through a family garden and nutrition program, leading to [Positive Impacts] (a) improved growth and development, (b) more active participation in family and community activities, and (c) better school attendance and performance increasing their ability to receive an education. This leads to an increase in their ability as adults to (d) lead the productive, meaningful, prosperous lives they need to leave the cycle of poverty and contribute to the development of their communities. |
|  |  | [Long-term positive outcome] Impact | 100 families in the western highlands of Guatemala have risen out of the cycle of poverty and lead healthy, prosperous, productive lives. |
| (1) Sub-Goal 1 (Objective) [sub-components of the main goal, which when added together describe the main goal] |
| Health and Hygiene Program | [Short-term positive outcome influencing mid-term positive outcome] 50% of the children from 100 families in 4 communities will be free of chronic diarrhea through a 12 month health and hygiene program | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] | 100 rural families adopt beneficial health and hygiene practices into their lives allowing children to grow and develop properly, be able to participate in education, and be prosperous, productive members of their communities. |
| Output 1.1 [sub-components of the sub-goal, which when added together describe the sub-goal] | 100 families in 4 communities participated in workshops on the benefits and practice of hand washing and received 6 months of follow up. | 100 families learn the health benefits and techniques of hand washing and adopt it for 6 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 1.1.1 | Develop workshop lesson plan; collect/develop workshop materials | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 1.1.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of attendance ; copy of schedule |  |
|  | Activity 1.1.3 | Present workshops to 100 families | Members of 100 families attend workshops on hand washing | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 1.1.4 | Provide 6 months follow-up | Families visited once a month for 6 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| Output 1.2 [sub-components of the sub-goal, which when added together describe the sub-goal] | 100 families in 4 communities participated in workshops on the benefits and practice of point of use water purification have; follow-up continued for 3 months | 100 families learn the health benefits and techniques of point of use water purification and adopt it for 3 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 1.2.1 | Develop workshop lesson plan; collect/develop workshop materials and SODIS bottles | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 1.2.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of sign-up sheet; copy of schedule |  |
|  | Activity 1.2.3 | Present workshops | Members of 100 families attend workshops on hand washing | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 1.2.4 | Provide 3 months follow-up | Families visited once a month for 3 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| (2) Sub-Goal 2 (Objective) [sub-components of the main goal, which when added together describe the main goal] |
| Family Garden and Nutrition Program [sub-components of the sub-goal, which when added together describe the sub-goal] | [Short-term positive outcome influencing mid-term positive outcome] 50% of 100 families and their children in four villages will be properly nourished and able to enjoy 12 months of food security per year through a 1 year family garden and nutrition program | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] | Rural families adopt good overall nutrition and food security practices into their lives through family gardens allowing children to grow and develop properly and be able to participate in education, and be prosperous, productive members of their communities. |
| Output 2.1 | 100 families in 4 communities participated in workshops on family nutrition and the benefits of planning and utilizing home gardens for family nutrition: 3 months follow-up | 100 families learn the health benefits and techniques of planning and utilizing home gardens for family nutrition and adopt it for 3 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 2.1.1 | Develop workshop lesson plan; collect/develop workshop materials | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 2.1.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of sign-up sheet; copy of schedule |  |
|  | Activity 2.1.3 | Present workshops | Members of 100 families attend workshops on hand washing | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 2.1.4 | Provide 3 months follow-up | Families visited once a month for 3 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| Output 2.2 [sub-components of the sub-goal, which when added together describe the sub-goal] | Workshops on planning, forming and planting home gardens for family nutrition have been presented to 100 families in 4 communities; each family has at least 1 productive bed of fruits and vegetables as a direct result of the workshop. Follow-up continued for 6 months. | 100 families learn the health benefits and techniques of starting home gardens for family nutrition and adopt it for 6 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 2.2.1 | Develop workshop lesson plan; collect/develop workshop materials | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 2.2.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of sign-up sheet; copy of schedule |  |
|  | Activity 2.2.3 | Present workshops | Members of 100 families attend workshops on hand washing | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 2.2.4 | Provide 6 months follow-up | Families visited once a month for 6 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |